## Gantt Chart Template
GANTT CHART | [27 empty] | https://goo.gl/PXLbMe
| Project Title | Detection of Suspicious Activities on Social Media Using Data Mining and Machine Learning. |  |  |  |  | Group Number | [8 empty] | Group 1:5 | [35 empty] | PHASE FOUR
| Group Leader | Krupaben Kothadia |  |  |  |  | Deputy Group Leader | [8 empty] | Gautham Vijayaraj
PHASE ONE
Task Number | Task Title | Task Assigned to | START DATE | DUE DATE | DURATION (in days) | Progress (Complete/InProgress) | WEEK 1 (08/21-08/27) |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
1 | Task Goal |  | (mm/dd/yy) | (mm/dd/yy)
#1.1 | Literature Review, Preparing Project Plan (References and Project Outcome), Evaluating 4 team members' Research Papers, Evaluating Gantt Chart, Preparing weekly report, Evaluating Work_Distribution_Draft file, Organizing Google Drive, Organizing Weekly Team Meeting, Collaborating and Creating a Group on Discord, Addressing Team Member’s Questions Regarding Project, Making Team Member Understand the Project Approach, Scope, Outcome and Definition | Krupaben Kothadia | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M
#1.2 | Literature Review, Preparing Project Plan (References and Project Outcome), Formatting Work Distribution Draft, Verified that all members have uploaded their respective files onto the shared drive, Evaluating 4 team members' Research Papers, Evaluating Gantt Chart, Approving weekly report | Gautham Vijayaraj | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M
#1.3 | Literature Review, Preparing Project Plan (Project Risk and References) | Avani Mundra | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M
#1.4 | Literature Review, Preparing Project Plan (Project risk) | Justin Young | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F
#1.5 | Literature Review, Searching for Datasets,Preparing Project Plan (References), Preparing Weekly Report | Anuranjan Dubey | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M
#1.6 | Literature Review, Preparing Project Plan (Creating Gantt Chart and References ) | Rahul Rajarama Nayak | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F
#1.7 | Literature Review, Preparing Project Plan (Project Scope), Data Collection | Sangeeth Santhosh | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M
#1.8 | Literature Review, Preparing Project Plan(Project Scope) | Yeshwanth Reddy Chennur | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M
2 | Task Goal | bar: WEEK 1 (08/21-08/27) M to WEEK 7 M; WEEK 7 W to WEEK 9 F
2.1 | Came up with 5 research papers on Data Preprocessing and NLP techniques to produce robust dataset for detecting suspicous activities on social media, preparing individual in-depth report, preparing individual progress report, evaluating Gautham’s individual progress report and in-depth report, preparing Project Plan and Gantt Chart, evaluating Weekly Report, approving 4 members in-depth reports, organizing group meeting, assigning tasks, providing direction in preparing Weekly Report, project plan and Gantt chart, and approving 4 members research domain and their research papers, organizing google drive. | Krupaben Kothadia | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 7 M
2.2 | Came up with 5 research papers on Secure Data Collection Techniques, preparing individual in-depth report, preparing individual progress report, evaluating Krupa’s individual progress report and in-depth report, preparing Weekly Report and project plan, evaluating Gantt chart, approving 4 members in-depth reports,providing guidance, organizing drive, addressing queries and approving 4 members research domain and their research papers. | Gautham Vijayaraj | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 7 M
2.3 | Came up with 3 research papers on Data Mining Techniques to Handle Multimodal Data, preparing individual in-depth report, preparing individual progress report, evaluating Yeshwanth’s individual progress report and in-depth report, preparing project plan. | Avani Mundra | 2023-08-29 | 2023-09-01 | 4 | Complete
2.4 | Came up with 4 research papers on Ensuring Model Security, preparing individual in-depth report, preparing individual progress report, evaluating Sangeeth’s individual progress report and in-depth report, preparing project plan and Gantt chart. | Justin Young | 2023-08-29 | 2023-09-01 | 4 | Complete
2.5 | Came up with 4 research papers on Leveraging Machine Learning Models for detection of suspicious activities on social media, preparing individual in-depth report, preparing individual progress report, evaluating Rahul’s individual progress report and in-depth report, preparing project plan. | Anuranjan Dubey | 2023-08-29 | 2023-09-01 | 4 | Complete
2.6 | Came up with 4 research papers on Data Exploration for varied suspicious activities, preparing individual in-depth report, preparing individual progress report, evaluating Avani’s individual progress report and in-depth report, preparing project plan. | Rahul Rajarama Nayak | 2023-08-29 | 2023-09-01 | 4 | Complete
2.7 | Came up with 5 research papers on Model Evaluation and, explainability of False negatives and Positives generated by Machine Learning Algorithms, preparing individual in-depth report, preparing individual progress report, preparing weekly report, evaluating Anuranjan’s individual progress report and in-depth report, preparing project plan. | Sangeeth Santhosh | 2023-08-29 | 2023-09-01 | 4 | Complete
2.8 | Came up with 3 research papers on the models that are self evolving and updated with real-time evolving threats, preparing individual in-depth report, preparing individual progress report, evaluating Justin’s individual progress report and in-depth report, preparing project plan. | Yeshwanth Reddy Chennur | 2023-08-29 | 2023-09-01 | 4 | Complete
3 | Task Goal | bar: WEEK 1 (08/21-08/27) M to WEEK 7 M; WEEK 7 W to WEEK 9 F
3.1 | Task Descripton | (Member Name) |  |  | 0 | Not Started | bar: WEEK 7 M
3.2 | Task Descripton | (Member Name) |  |  | 0 | Not Started | bar: WEEK 7 M
3.3 | Task Descripton | (Member Name) |  |  | 0 | Not Started | bar: WEEK 7 M
3.4 | Task Descripton | (Member Name) |  |  | 0 | Not Started
3.5 | Task Descripton | (Member Name) |  |  | 0 | Not Started
3.6 | Task Descripton | (Member Name) |  |  | 0 | Not Started | bar: WEEK 7 M
3.7 | Task Descripton | (Member Name) |  |  | 0 | Not Started | bar: WEEK 7 M
3.8 | Task Descripton | (Member Name) |  |  | 0 | Not Started | bar: WEEK 7 M
4 | bar: WEEK 1 (08/21-08/27) M to WEEK 7 M; WEEK 7 W to WEEK 9 F
4.1 | Task Descripton | (Member Name) |  |  | 0 | Not Started | bar: WEEK 7 M
4.2 | Task Descripton | (Member Name) |  |  | 0 | Not Started | bar: WEEK 7 M
4.3 | Task Descripton | (Member Name) |  |  | 0 | Not Started
4.4 | Task Descripton | (Member Name) |  |  | 0 | Not Started