## Group 1-5  Weekly Report - #2

## List of members

Group Leader: Krupaben Kothadia

Group Deputy Leader: Gautham Vijayaraj

Group Members: Krupaben Kothadia

- Avani Mundra

- Justin Young

- Anuranjan Dubey

- Rahul Nayak

- Sangeeth Santhosh

- Yeshwanth Reddy Chennur

- Gautham Vijayaraj

## Submission Details

Name of member that prepared the report:  Rahul NayakJustin Young

Name of member that submitted this report: Gautham Vijayaraj
Report is approved by: Krupaben Kothadia Gautham Vijayaraj

## Meeting Notes

09/05/23 - 6:00 p.m.  (Mode: Online)

- Meeting Objective: Discuss the overall progress of the project,Addressing questions related to adding additional reference papers, discussing an approach to continue the in-depth progress reports, addressing questions and providing information to team members,discussing formatting related questions,  task discussion and distribution for project plan.

- Members present: Krupaben Kothadia Justin Young Rahul Nayak Sangeeth Santhosh
 Yeshwanth Reddy Chennur Gautham Vijayaraj Anuranjan Dubey

- Members absent: Avani Mundra

- Reason for absence: Traveling

- Discussion:

  - Evaluated the project's overall advancement, considering the key milestones and objectives achieved thus far.

  - Addressed queries pertaining to the inclusion of supplementary reference materials, discussing their relevance and potential impact on project outcomes.

  - Outlined a systematic approach for formatting in-depth progress reports, defining the structure and content requirements.

  - Efficiently distributed tasks and responsibilities within the project plan.

  - Effectively resolved inquiries related to individual reports, weekly progress updates, and references, ensuring clarity and accuracy in project documentation.

- To Do List:

  - Each team member will be responsible for preparing their individual in-depth report (if any) for a reference paper they have collected.

  - Each team member will be responsible for preparing their individual progress report.

  - Each member will be responsible for evaluating another member’s individual progress reports.

  - Team leader and deputy leader will be responsible for approving 4 individual progress reports.

  - Team leader will organize the Google Drive and keep track of member’s progress and completion of tasks.

  - Team members on this week’s rotation will prepare the Gantt chart and weekly reports.

- Next Meeting Scheduled on: 09/12/23 - 6:00 p.m.

## Individual Progress Reports and In-Depth Reports

| Member Name | Weekly Member Progress Link | Individual In-Depth Reports Link | Self Acknowledgement | Evaluator Acknowledgement |
| --- | --- | --- | --- | --- |
| Krupaben Kothadia | Individual progress report |  | Krupaben Kothadia | Gautham Vijayaraj |
| Gautham Vijayaraj | Individual Progress Report | Individual In-Depth Report | Gautham Vijayaraj | Krupaben Kothadia |
| Avani Mundra | Individual Progress report |  | Avani Mundra | Rahul Nayak Krupaben Kothadia |
| Justin Young | Individual Progress report | Individual In-Depth Report | Justin Young | Yeshwanth Reddy Chennur Krupaben Kothadia |
| Anuranjan Dubey | Individual Progress report | Individual In-Depth Report | Anuranjan Dubey | Sangeeth Santhosh Krupaben Kothadia |
| Rahul Nayak | Individual Progress report | Individual In-Depth report | Rahul Nayak | Anuranjan Dubey Gautham Vijayaraj |
| Sangeeth Santhosh | Individual Progress report | Individual In-Depth Report | Sangeeth Santhosh | Justin Young Gautham Vijayaraj |
| Yeshwanth Reddy Chennur | Individual Progress report |  | Yeshwanth Reddy Chennur | Avani Mundra Gautham Vijayaraj |

## Tasks Summary

| Task Number | Task Goal | Description of Task | Assignee | Task Status | Evaluator |
| --- | --- | --- | --- | --- | --- |
| #3.1 | Individual progress report, Evaluation and approval of reports, Gantt chart evaluation and approval, weekly report evaluation and approval, team meetings, organize Google Drive | Preparing individual progress report,evaluating Gautham’s individual progress report and in-depth report,evaluating Weekly Report,Gantt chart, Approving 4 members in-depth reports, organizing group meetings, assigning tasks, organizing google drive. | Krupaben Kothadia | Completed | Gautham Vijayaraj |
| #3.2 | In-depth report, individual progress report, prepare Gantt chart, weekly report evaluation and approval, Evaluation and approval of reports, taking meeting notes, organize Google Drive | Preparing In depth report,Preparing individual progress report,evaluating Krupaben Kothadia’s individual progress report and in-depth report,evaluating Weekly Report,Preparing Gantt chart, Taking meeting notes, organizing google drive, Approving 4 members in-depth reports. | Gautham Vijayaraj | Completed | Krupaben Kothadia |
| #3.3 | In-depth report, individual progress report, evaluation of reports | Preparing In depth report,Preparing individual progress report ,Evaluating Yeshwanth Reddy Chennur’s In depth and progress reports. | Avani Mundra | Completed | Krupaben Kothadia |
| #3.4 | In-depth report, individual progress report, evaluation of reports, prepare weekly report | Preparing In depth report,Preparing individual progress report,Preparing weekly Report, Evaluating Sangeeth Santhosh’s In depth and progress reports. | Justin Young | Completed | Krupaben Kothadia |
| #3.5 | In-depth report, individual progress report, evaluation of reports | Preparing In depth report,Preparing individual progress report,Evaluating Rahul Nayak’s In depth and progress reports. | Anuranjan Dubey | Completed | Krupaben Kothadia |
| #3.6 | In-depth report, individual progress report, evaluation of reports, prepare weekly report | Preparing In depth report,Preparing individual progress report, Preparing Weekly report, Evaluating Avani Mundra’s In depth and progress reports. | Rahul Nayak | Completed | Gautham Vijayaraj |
| #3.7 | In-depth report, individual progress report, evaluation of reports | Preparing In depth report,Preparing individual progress report, Evaluating Anuranjan Dubey’s In depth and progress reports. | Sangeeth Santhosh | Completed | Gautham Vijayaraj |
| #3.8 | In-depth report, individual progress report, evaluation of reports | Preparing In depth report,Preparing individual progress report,Evaluating Justin Young’s In depth and progress reports. | Yeshwanth Reddy Chennur | Completed | Gautham Vijayaraj |

## Gantt chart

Link to the gantt chart: Gantt Chart

Gantt chart updated by:  Gautham Vijayaraj

Gantt chart approved by:  Krupaben Kothadia

## Comments

- All group members have been cooperative, showed enthusiasm to work on a project, and have put in an effort to complete their assigned tasks successfully this week.