## Gantt Chart Template
GANTT CHART | [27 empty] | https://goo.gl/PXLbMe
| Project Title | Detection of Suspicious Activities on Social Media Using Data Mining and Machine Learning. |  |  |  |  | Group Number | [8 empty] | Group 1:5 | [35 empty] | PHASE FOUR
| Group Leader | Krupaben Kothadia |  |  |  |  | Deputy Group Leader | [8 empty] | Gautham Vijayaraj
PHASE ONE
Task Number | Task Title | Task Assigned to | START DATE | DUE DATE | DURATION (in days) | Progress (Complete/InProgress) | WEEK 1 (08/21-08/27) |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
1 | Task Goal |  | (mm/dd/yy) | (mm/dd/yy)
#1.1 | Literature Review, Preparing Project Plan (References and Project Outcome), Evaluating 4 team members' Research Papers, Evaluating Gantt Chart, Preparing weekly report, Evaluating Work_Distribution_Draft file, Organizing Google Drive, Organizing Weekly Team Meeting, Collaborating and Creating a Group on Discord, Addressing Team Member’s Questions Regarding Project, Making Team Member Understand the Project Approach, Scope, Outcome and Definition | Krupaben Kothadia | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.2 | Literature Review, Preparing Project Plan (References and Project Outcome), Formatting Work Distribution Draft, Verified that all members have uploaded their respective files onto the shared drive, Evaluating 4 team members' Research Papers, Evaluating Gantt Chart, Approving weekly report | Gautham Vijayaraj | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.3 | Literature Review, Preparing Project Plan (Project Risk and References) | Avani Mundra | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.4 | Literature Review, Preparing Project Plan (Project risk) | Justin Young | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.5 | Literature Review, Searching for Datasets,Preparing Project Plan (References), Preparing Weekly Report | Anuranjan Dubey | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.6 | Literature Review, Preparing Project Plan (Creating Gantt Chart and References ) | Rahul Rajarama Nayak | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.7 | Literature Review, Preparing Project Plan (Project Scope), Data Collection | Sangeeth Santhosh | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.8 | Literature Review, Preparing Project Plan(Project Scope) | Yeshwanth Reddy Chennur | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
2 | Task Goal | bar: WEEK 1 (08/21-08/27) M to WEEK 9 F
#2.1 | Came up with 5 research papers on Data Preprocessing and NLP techniques to produce robust dataset for detecting suspicious activities on social media, preparing individual in-depth report, preparing individual progress report, evaluating Gautham’s individual progress report and in-depth report, preparing Project Plan and Gantt Chart, evaluating Weekly Report, approving 4 members in-depth reports, organizing group meeting, assigning tasks, providing direction in preparing Weekly Report, project plan and Gantt chart, and approving 4 members research domain and their research papers, organizing google drive. | Krupaben Kothadia | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.2 | Came up with 5 research papers on Secure Data Collection Techniques, preparing individual in-depth report, preparing individual progress report, evaluating Krupa’s individual progress report and in-depth report, preparing Weekly Report and project plan, evaluating Gantt chart, approving 4 members in-depth reports, and approving 4 members research domain and their research papers. | Gautham Vijayaraj | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.3 | Came up with 3 research papers on Data Mining Techniques to Handle Multimodal Data, preparing individual in-depth report, preparing individual progress report, evaluating Yeshwanth’s individual progress report and in-depth report, preparing project plan. | Avani Mundra | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.4 | Came up with 4 research papers on Ensuring Model Security, preparing individual in-depth report, preparing individual progress report, evaluating Sangeeth’s individual progress report and in-depth report, preparing project plan and Gantt chart. | Justin Young | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.5 | Came up with 4 research papers on Leveraging Machine Learning Models for detection of suspicious activities on social media, preparing individual in-depth report, preparing individual progress report, evaluating Rahul’s individual progress report and in-depth report, preparing project plan. | Anuranjan Dubey | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.6 | Came up with 4 research papers on Data Exploration for varied suspicious activities, preparing individual in-depth report, preparing individual progress report, evaluating Avani’s individual progress report and in-depth report, preparing project plan. | Rahul Rajarama Nayak | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.7 | Came up with 5 research papers on Model Evaluation and, explainability of False negatives and Positives generated by Machine Learning Algorithms, preparing individual in-depth report, preparing individual progress report, evaluating Avani’s individual progress report and in-depth report, preparing project plan. | Sangeeth Santhosh | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.8 | Came up with 3 research papers on the models that are self evolving and updated with real-time evolving threats, preparing individual in-depth report, preparing individual progress report, evaluating Avani’s individual progress report and in-depth report, preparing project plan. | Yeshwanth Reddy Chennur | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
3 | Task Goal | bar: WEEK 1 (08/21-08/27) M to WEEK 9 F
#3.1 | Preparing In depth report,Preparing individual progress report,evaluating Gautham’s individual progress report and in-depth report,evaluating Weekly Report,Gantt chart, Approving 4 members in-depth reports, organizing group meeting, assigning tasks, organizing google drive. | Krupaben Kothadia | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.2 | Preparing In depth report,Preparing individual progress report,evaluating Krupaben Kothadia’s individual progress report and in-depth report,evaluating Weekly Report,Preparing Gantt chart, Taking meeting notes, Organzing Google Drive, Approving 4 members in-depth reports. | Gautham Vijayaraj | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.3 | Preparing In depth report,Preparing individual progress report ,Evaluating Yeshwanth Reddy Chennur’s In depth and progress reports. | Avani Mundra | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.4 | Preparing In depth report,Preparing individual progress report,Preparing weekly Report, Evaluating Sangeeth Santhosh’s In depth and progress reports. In depth and progress reports. | Justin Young | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.5 | Preparing In depth report,Preparing individual progress report,Evaluating Rahul Nayak’s In depth and progress reports. | Anuranjan Dubey | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.6 | Preparing In depth report,Preparing individual progress report, Preparing Weekly report, Evaluating Avani Mundra’s In depth and progress reports. In depth and progress reports. | Rahul Rajarama Nayak | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.7 | Preparing In depth report,Preparing individual progress report, Evaluating Anuranjan Dubey’s In depth and progress reports. | Sangeeth Santhosh | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.8 | Preparing In depth report,Preparing individual progress report,Evaluating Justin Young’s In depth and progress reports. | Yeshwanth Reddy Chennur | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
4 | Task Goal | bar: WEEK 1 (08/21-08/27) M to WEEK 9 F
#4.1 | Visiting Writing Center, Preparing References_List document, Preparing Work_Distribution_Draft, Preparing individual in-depth report, Preparing individual progress report, Evaluating Gautham’s individual progress report and in-depth report, Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Evaluating and approving 4 team members’ individual progress reports, Assigning the task distribution, Providing a summary of content for the weekly report and GANTT Chart, Organizing group meetings, Organizing google drive. Refer paper [12] from References_List. | Krupaben Kothadia | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#4.2 | Preparing References_List doc, Preparing individual in-depth report, Preparing individual progress report, Evaluating Krupaben Kothadia’s individual progress report and in-depth report, Evaluating and approving GANTT Chart, Preparing Weekly Report (Add References_List doc link), Evaluating and approving 4 team members’ individual progress reports, Taking meeting notes. Refer paper [9] from References_List | Gautham Vijayaraj | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#4.3 | Preparing individual progress report, Preparing individual in-depth report, Evaluating Yeshwanth Reddy Chennur’s In depth and progress reports. Refer paper [15] from References_List | Avani Mundra | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#4.4 | Preparing individual progress report, Preparing individual in-depth report, Evaluating Sangeeth Santhosh’s In depth and progress reports. Refer paper [28] from References_List | Justin Young | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#4.5 | Preparing individual progress report, Preparing individual in-depth report, Evaluating in-depth report of Rahul Rajaram Nayak, Evaluating Rahul Rajaram Nayak's individual progress reports, Preparing GANTT Chart, Refer paper [21] from References_List. | Anuranjan Dubey | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F
#4.6 | Preparing individual progress report, Preparing individual in-depth report, Evaluating Avani Mundra's in-depth report, Evaluating Avni Mundra's individual progress reports,Refer paper [2] from References_List. | Rahul Rajarama Nayak | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F
#4.7 | Preparing individual progress report, Preparing individual in-depth report, Evaluating Anuranjan Dubey's in-depth report, Evaluating Anuranjan Dubey's individual progress reports,Refer paper [31] from References_List. | Sangeeth Santhosh | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F
#4.8 | Preparing individual progress report, Preparing individual in-depth report, Evaluating in-depth report of Justin Young , Evaluating Justin Young's individual progress reports, Preparing Weekly Report (Add References_List doc link),Refer paper [25] from References_List. | Yeshwanth Reddy Chennur | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F
5 | Task Goal
#5.1 | Preparing Midterm report, Preparing individual midterm review report, Preparing Work_Distribution_Draft, Preparing GANTT Chart, Preparing individual in-depth report, Preparing individual progress report, Evaluating and approving Weekly report and Midterm report, Evaluating and approving 4 team members’ individual progress and in-depth reports, Assigning the task distribution, Providing a rough draft of content for the midterm report, weekly report and GANTT Chart, Organizing group meetings, Organizing google drive. In-depth report on Refer paper [13] from References_List. | Krupaben Kothadia | 2023-09-19 | 2023-09-25 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.2 | Preparing Midterm report, Preparing individual midterm review report, Visiting Writing Center, Preparing individual in-depth report, Preparing individual progress report, Evaluating and approving 4 team members’ individual progress and in-depth reports, Evaluating and approving Midterm Report , Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Format for Mid term report,Taking meeting notes. In-depth report on Refer paper [6] from References_List. | Gautham Vijayaraj | 2023-09-20 | 2023-09-26 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.3 | Preparing Midterm report, Preparing individual midterm review report, Preparing weekly report, Preparing individual progress report, Preparing individual in-depth report, Evaluating 1 team member’s individual progress and in-depth reports. In-depth report on Refer paper [37] from References_List. | Avani Mundra | 2023-09-21 | 2023-09-27 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.4 | Preparing Midterm report, Preparing individual midterm review report, Preparing weekly report, Preparing individual progress report, Preparing individual in-depth report, Evaluating 1 team member’s individual progress and in-depth reports. In-depth report on Refer paper [30] from References_List. | Justin Young | 2023-09-22 | 2023-09-28 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.5 | Preparing Midterm report, Preparing individual midterm review report, Preparing individual progress report, Preparing individual in-depth report, Evaluating 1 team member’s individual progress and in-depth reports. In-depth report on Refer paper [22] from References_List. | Anuranjan Dubey | 2023-09-23 | 2023-09-29 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.6 | Preparing Midterm report, Preparing individual midterm review report, Preparing individual progress report, Evaluating 1 team member’s individual progress and in-depth reports. | Rahul Rajarama Nayak | 2023-09-24 | 2023-09-30 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.7 | Preparing Midterm report, Preparing individual midterm review report, Preparing individual progress report, Preparing individual in-depth report, Evaluating 1 team member’s individual progress and in-depth reports. In-depth report on Refer paper [32] from References_List. | Sangeeth Santhosh | 2023-09-25 | 2023-10-01 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.8 | Preparing Midterm report, Preparing individual midterm review report, Preparing individual progress report, Evaluating 1 team member’s individual progress and in-depth reports. | Yeshwanth Reddy Chennur | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
6 | Task Goal
#6.1 | Preparing Work_Distribution_Draft,Preparing individual in-depth report on refer paper [11],Preparing individual progress report, Evaluating and approving 4 team members’ individual progress and in-depth reports,Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Assigning the task distribution,Providing summary of content for weekly report and GANTT Chart,Organizing group meetings, Organizing google drive | Krupaben Kothadia | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.2 | Preparing individual in-depth report on refer paper[8], preparing individual progress report, evaluating and approving 4 team members’ individual progress and in-depth reports, evaluating and approving GANTT Chart, evaluating and approving Weekly Report, organizing group meetings, taking meeting notes. | Gautham Vijayaraj | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.3 | Preparing individual progress report, preparing individual in-depth report on refer paper, evaluating one team member’s individual progress and in-depth reports. | Avani Mundra | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.4 | Visiting Writing Center, preparing Weekly Report , preparing individual progress report, preparing individual in-depth report on refer paper[39], evaluating one team member’s individual progress and in-depth reports. | Justin Young | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.5 | Searching for additional research papers (Extending to other social media platforms.), preparing individual progress report, preparing individual in-depth report on refer paper[38], evaluating one team member’s individual progress and in-depth reports. | Anuranjan Dubey | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.6 | Preparing GANTT Chart, preparing individual progress report, preparing individual in-depth report on refer paper[1], evaluating one team member’s individual progress and in-depth reports. | Rahul Rajarama Nayak | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.7 | Preparing Weekly Report , preparing individual progress report, preparing individual in-depth report on refer paper[33], evaluating one team member’s individual progress and in-depth reports. | Sangeeth Santhosh | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.8 | Preparing individual progress report, preparing 2 individual in-depth reports on refer papers[36] and [19], evaluating one team member’s individual progress and in-depth reports. | Yeshwanth Reddy Chennur | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F