## Gantt Chart Template
GANTT CHART | [27 empty] | https://goo.gl/PXLbMe
| Project Title | Detection of Suspicious Activities on Social Media Using Data Mining and Machine Learning. |  |  |  |  | Group Number | [8 empty] | Group 1:5 | [35 empty] | PHASE FOUR
| Group Leader | Krupaben Kothadia |  |  |  |  | Deputy Group Leader | [8 empty] | Gautham Vijayaraj
PHASE ONE
Task Number | Task Title | Task Assigned to | START DATE | DUE DATE | DURATION (in days) | Progress (Complete/InProgress) | WEEK 1 (08/21-08/27) |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
1 | Task Goal |  | (mm/dd/yy) | (mm/dd/yy)
#1.1 | Literature Review, Preparing Project Plan (References and Project Outcome), Evaluating 4 team members' Research Papers, Evaluating Gantt Chart, Preparing weekly report, Evaluating Work_Distribution_Draft file, Organizing Google Drive, Organizing Weekly Team Meeting, Collaborating and Creating a Group on Discord, Addressing Team Member’s Questions Regarding Project, Making Team Member Understand the Project Approach, Scope, Outcome and Definition | Krupaben Kothadia | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.2 | Literature Review, Preparing Project Plan (References and Project Outcome), Formatting Work Distribution Draft, Verified that all members have uploaded their respective files onto the shared drive, Evaluating 4 team members' Research Papers, Evaluating Gantt Chart, Approving weekly report | Gautham Vijayaraj | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.3 | Literature Review, Preparing Project Plan (Project Risk and References) | Avani Mundra | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.4 | Literature Review, Preparing Project Plan (Project risk) | Justin Young | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.5 | Literature Review, Searching for Datasets,Preparing Project Plan (References), Preparing Weekly Report | Anuranjan Dubey | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.6 | Literature Review, Preparing Project Plan (Creating Gantt Chart and References ) | Rahul Rajarama Nayak | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.7 | Literature Review, Preparing Project Plan (Project Scope), Data Collection | Sangeeth Santhosh | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#1.8 | Literature Review, Preparing Project Plan(Project Scope) | Yeshwanth Reddy Chennur | 2023-08-21 | 2023-08-27 | 6 | Complete | bar: WEEK 1 (08/21-08/27) M to WEEK 2 F; WEEK 7 M to WEEK 7 F
2 | Task Goal | bar: WEEK 1 (08/21-08/27) M to WEEK 9 F
#2.1 | Came up with 5 research papers on Data Preprocessing and NLP techniques to produce robust dataset for detecting suspicious activities on social media, preparing individual in-depth report, preparing individual progress report, evaluating Gautham’s individual progress report and in-depth report, preparing Project Plan and Gantt Chart, evaluating Weekly Report, approving 4 members in-depth reports, organizing group meeting, assigning tasks, providing direction in preparing Weekly Report, project plan and Gantt chart, and approving 4 members research domain and their research papers, organizing google drive. | Krupaben Kothadia | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.2 | Came up with 5 research papers on Secure Data Collection Techniques, preparing individual in-depth report, preparing individual progress report, evaluating Krupa’s individual progress report and in-depth report, preparing Weekly Report and project plan, evaluating Gantt chart, approving 4 members in-depth reports, and approving 4 members research domain and their research papers. | Gautham Vijayaraj | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.3 | Came up with 3 research papers on Data Mining Techniques to Handle Multimodal Data, preparing individual in-depth report, preparing individual progress report, evaluating Yeshwanth’s individual progress report and in-depth report, preparing project plan. | Avani Mundra | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.4 | Came up with 4 research papers on Ensuring Model Security, preparing individual in-depth report, preparing individual progress report, evaluating Sangeeth’s individual progress report and in-depth report, preparing project plan and Gantt chart. | Justin Young | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.5 | Came up with 4 research papers on Leveraging Machine Learning Models for detection of suspicious activities on social media, preparing individual in-depth report, preparing individual progress report, evaluating Rahul’s individual progress report and in-depth report, preparing project plan. | Anuranjan Dubey | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.6 | Came up with 4 research papers on Data Exploration for varied suspicious activities, preparing individual in-depth report, preparing individual progress report, evaluating Avani’s individual progress report and in-depth report, preparing project plan. | Rahul Rajarama Nayak | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.7 | Came up with 5 research papers on Model Evaluation and, explainability of False negatives and Positives generated by Machine Learning Algorithms, preparing individual in-depth report, preparing individual progress report, evaluating Avani’s individual progress report and in-depth report, preparing project plan. | Sangeeth Santhosh | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#2.8 | Came up with 3 research papers on the models that are self evolving and updated with real-time evolving threats, preparing individual in-depth report, preparing individual progress report, evaluating Avani’s individual progress report and in-depth report, preparing project plan. | Yeshwanth Reddy Chennur | 2023-08-29 | 2023-09-01 | 4 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
3 | Task Goal | bar: WEEK 1 (08/21-08/27) M to WEEK 9 F
#3.1 | Preparing In depth report,Preparing individual progress report,evaluating Gautham’s individual progress report and in-depth report,evaluating Weekly Report,Gantt chart, Approving 4 members in-depth reports, organizing group meeting, assigning tasks, organizing google drive. | Krupaben Kothadia | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.2 | Preparing In depth report,Preparing individual progress report,evaluating Krupaben Kothadia’s individual progress report and in-depth report,evaluating Weekly Report,Preparing Gantt chart, Taking meeting notes, Organzing Google Drive, Approving 4 members in-depth reports. | Gautham Vijayaraj | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.3 | Preparing In depth report,Preparing individual progress report ,Evaluating Yeshwanth Reddy Chennur’s In depth and progress reports. | Avani Mundra | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.4 | Preparing In depth report,Preparing individual progress report,Preparing weekly Report, Evaluating Sangeeth Santhosh’s In depth and progress reports. In depth and progress reports. | Justin Young | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.5 | Preparing In depth report,Preparing individual progress report,Evaluating Rahul Nayak’s In depth and progress reports. | Anuranjan Dubey | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.6 | Preparing In depth report,Preparing individual progress report, Preparing Weekly report, Evaluating Avani Mundra’s In depth and progress reports. In depth and progress reports. | Rahul Rajarama Nayak | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.7 | Preparing In depth report,Preparing individual progress report, Evaluating Anuranjan Dubey’s In depth and progress reports. | Sangeeth Santhosh | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
#3.8 | Preparing In depth report,Preparing individual progress report,Evaluating Justin Young’s In depth and progress reports. | Yeshwanth Reddy Chennur | 2023-09-05 | 2023-09-11 | 6 | Complete | bar: WEEK 2 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
4 | Task Goal | bar: WEEK 1 (08/21-08/27) M to WEEK 9 F
#4.1 | Visiting Writing Center, Preparing References_List document, Preparing Work_Distribution_Draft, Preparing individual in-depth report, Preparing individual progress report, Evaluating Gautham’s individual progress report and in-depth report, Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Evaluating and approving 4 team members’ individual progress reports, Assigning the task distribution, Providing a summary of content for the weekly report and GANTT Chart, Organizing group meetings, Organizing google drive. Refer paper [12] from References_List. | Krupaben Kothadia | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#4.2 | Preparing References_List doc, Preparing individual in-depth report, Preparing individual progress report, Evaluating Krupaben Kothadia’s individual progress report and in-depth report, Evaluating and approving GANTT Chart, Preparing Weekly Report (Add References_List doc link), Evaluating and approving 4 team members’ individual progress reports, Taking meeting notes. Refer paper [9] from References_List | Gautham Vijayaraj | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#4.3 | Preparing individual progress report, Preparing individual in-depth report, Evaluating Yeshwanth Reddy Chennur’s In depth and progress reports. Refer paper [15] from References_List | Avani Mundra | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#4.4 | Preparing individual progress report, Preparing individual in-depth report, Evaluating Sangeeth Santhosh’s In depth and progress reports. Refer paper [28] from References_List | Justin Young | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 7 F
#4.5 | Preparing individual progress report, Preparing individual in-depth report, Evaluating in-depth report of Rahul Rajaram Nayak, Evaluating Rahul Rajaram Nayak's individual progress reports, Preparing GANTT Chart, Refer paper [21] from References_List. | Anuranjan Dubey | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F
#4.6 | Preparing individual progress report, Preparing individual in-depth report, Evaluating Avani Mundra's in-depth report, Evaluating Avni Mundra's individual progress reports,Refer paper [2] from References_List. | Rahul Rajarama Nayak | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F
#4.7 | Preparing individual progress report, Preparing individual in-depth report, Evaluating Anuranjan Dubey's in-depth report, Evaluating Anuranjan Dubey's individual progress reports,Refer paper [31] from References_List. | Sangeeth Santhosh | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F
#4.8 | Preparing individual progress report, Preparing individual in-depth report, Evaluating in-depth report of Justin Young , Evaluating Justin Young's individual progress reports, Preparing Weekly Report (Add References_List doc link),Refer paper [25] from References_List. | Yeshwanth Reddy Chennur | 2023-09-12 | 2023-09-18 | 6 | Complete | bar: WEEK 2 M to WEEK 2 F
5 | Task Goal
#5.1 | Preparing Midterm report, Preparing individual midterm review report, Preparing Work_Distribution_Draft, Preparing GANTT Chart, Preparing individual in-depth report, Preparing individual progress report, Evaluating and approving Weekly report and Midterm report, Evaluating and approving 4 team members’ individual progress and in-depth reports, Assigning the task distribution, Providing a rough draft of content for the midterm report, weekly report and GANTT Chart, Organizing group meetings, Organizing google drive. In-depth report on Refer paper [13] from References_List. | Krupaben Kothadia | 2023-09-19 | 2023-09-25 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.2 | Preparing Midterm report, Preparing individual midterm review report, Visiting Writing Center, Preparing individual in-depth report, Preparing individual progress report, Evaluating and approving 4 team members’ individual progress and in-depth reports, Evaluating and approving Midterm Report , Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Format for Mid term report,Taking meeting notes. In-depth report on Refer paper [6] from References_List. | Gautham Vijayaraj | 2023-09-20 | 2023-09-26 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.3 | Preparing Midterm report, Preparing individual midterm review report, Preparing weekly report, Preparing individual progress report, Preparing individual in-depth report, Evaluating 1 team member’s individual progress and in-depth reports. In-depth report on Refer paper [37] from References_List. | Avani Mundra | 2023-09-21 | 2023-09-27 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.4 | Preparing Midterm report, Preparing individual midterm review report, Preparing weekly report, Preparing individual progress report, Preparing individual in-depth report, Evaluating 1 team member’s individual progress and in-depth reports. In-depth report on Refer paper [30] from References_List. | Justin Young | 2023-09-22 | 2023-09-28 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.5 | Preparing Midterm report, Preparing individual midterm review report, Preparing individual progress report, Preparing individual in-depth report, Evaluating 1 team member’s individual progress and in-depth reports. In-depth report on Refer paper [22] from References_List. | Anuranjan Dubey | 2023-09-23 | 2023-09-29 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.6 | Preparing Midterm report, Preparing individual midterm review report, Preparing individual progress report, Evaluating 1 team member’s individual progress and in-depth reports. | Rahul Rajarama Nayak | 2023-09-24 | 2023-09-30 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.7 | Preparing Midterm report, Preparing individual midterm review report, Preparing individual progress report, Preparing individual in-depth report, Evaluating 1 team member’s individual progress and in-depth reports. In-depth report on Refer paper [32] from References_List. | Sangeeth Santhosh | 2023-09-25 | 2023-10-01 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
#5.8 | Preparing Midterm report, Preparing individual midterm review report, Preparing individual progress report, Evaluating 1 team member’s individual progress and in-depth reports. | Yeshwanth Reddy Chennur | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 5 M to WEEK 5 F
6 | Task Goal
#6.1 | Preparing Work_Distribution_Draft,Preparing individual in-depth report on refer paper [11],Preparing individual progress report, Evaluating and approving 4 team members’ individual progress and in-depth reports,Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Assigning the task distribution,Providing summary of content for weekly report and GANTT Chart,Organizing group meetings, Organizing google drive | Krupaben Kothadia | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.2 | Preparing individual in-depth report on refer paper[8], preparing individual progress report, evaluating and approving 4 team members’ individual progress and in-depth reports, evaluating and approving GANTT Chart, evaluating and approving Weekly Report, organizing group meetings, taking meeting notes. | Gautham Vijayaraj | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.3 | Preparing individual progress report, preparing individual in-depth report, evaluating one team member’s individual progress and in-depth reports. Preparing individual in-depth report on refer paper[40] | Avani Mundra | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.4 | Visiting Writing Center, preparing Weekly Report , preparing individual progress report, preparing individual in-depth report on refer paper[39], evaluating one team member’s individual progress and in-depth reports. | Justin Young | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.5 | Searching for additional research papers (Extending to other social media platforms.), preparing individual progress report, preparing individual in-depth report on refer paper[38], evaluating one team member’s individual progress and in-depth reports. | Anuranjan Dubey | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.6 | Preparing GANTT Chart, preparing individual progress report, preparing individual in-depth report on refer paper[1], evaluating one team member’s individual progress and in-depth reports. | Rahul Rajarama Nayak | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.7 | Preparing Weekly Report , preparing individual progress report, preparing individual in-depth report on refer paper[33], evaluating one team member’s individual progress and in-depth reports. | Sangeeth Santhosh | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
#6.8 | Preparing individual progress report, preparing 2 individual in-depth reports on refer papers[36] and [19], evaluating one team member’s individual progress and in-depth reports. | Yeshwanth Reddy Chennur | 2023-09-26 | 2023-10-02 | 6 | Complete | bar: WEEK 6 M to WEEK 6 F
7 | Task Goal
#7.1 | Preparing Weekly Report, Preparing Work_Distribution_Draft, Preparing individual in-depth report on refer paper [14], Preparing individual progress report, Evaluating and approving team members’ individual progress and in-depth reports, Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Assigning the task distribution, Providing summary of content for weekly report and GANTT Chart, Organizing group meetings, Organizing google drive. | Krupaben Kothadia | 2023-10-03 | 2023-10-09 | 6 | Complete | bar: WEEK 7 M to WEEK 7 F
#7.2 | Preparing Weekly Report, Preparing individual progress report, Evaluating and approving team members’ individual progress and in-depth reports, Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Taking meeting notes, Assigning the task distribution | Gautham Vijayaraj | 2023-10-03 | 2023-10-09 | 6 | Complete | bar: WEEK 7 M to WEEK 7 F
#7.3 | Preparing individual progress report, Preparing individual in-depth report on refer paper [41], Evaluating one team member’s individual progress and in-depth reports. | Avani Mundra | 2023-10-03 | 2023-10-09 | 6 | Complete | bar: WEEK 7 M to WEEK 7 F
#7.4 | Preparing individual progress report, Evaluating one team member’s individual progress, studying not-so-important papers. | Justin Young | 2023-10-03 | 2023-10-09 | 6 | Complete | bar: WEEK 7 M to WEEK 7 F
#7.5 | Visiting Writing Center, Preparing individual progress report, Evaluating one team member’s individual progress and studying not-so-important papers. | Anuranjan Dubey | 2023-10-03 | 2023-10-09 | 6 | Complete | bar: WEEK 7 M to WEEK 7 F
#7.6 | Preparing individual progress report, Evaluating one team member’s individual progress and in-depth reports. | Rahul Rajarama Nayak | 2023-10-03 | 2023-10-09 | 6 | Complete | bar: WEEK 7 M to WEEK 7 F
#7.7 | Visiting Writing Center, Preparing individual progress report, Evaluating one team member’s individual progress. | Sangeeth Santhosh | 2023-10-03 | 2023-10-09 | 6 | Complete | bar: WEEK 7 M to WEEK 7 F
#7.8 | Preparing GANTT Chart, Preparing individual progress report, Preparing individual in-depth report on refer paper [25], Evaluating one team member’s individual progress. | Yeshwanth Reddy Chennur | 2023-10-03 | 2023-10-09 | 6 | Complete | bar: WEEK 7 M to WEEK 7 F
8 | Task Goal
#8.1 | Preparing Weekly Report, Preparing Work_Distribution_Draft, Preparing individual in-depth report on refer paper [43],refer paper [44] Preparing individual progress report, Evaluating and approving team members’ individual progress and in-depth reports, Evaluating and approving GANTT Chart, Evaluating and approving Weekly Report, Assigning the task distribution, Providing summary of content for weekly report and GANTT Chart, Organizing group meetings, Organizing google drive. | Krupaben Kothadia | 2023-10-10 | 2023-10-16 | 6 | Complete | bar: WEEK 8 M to WEEK 8 F
#8.2 | Preparing an individual progress report, in-depth report [46], study progress report, evaluating and approving team members’ individual progress and in-depth reports, evaluating and approving GANTT Chart, evaluating and approving Weekly Report, taking meeting notes, assigning the task distribution, reading Not so important papers, organizing google drive. | Gautham Vijayaraj | 2023-10-10 | 2023-10-16 | 6 | Complete | bar: WEEK 8 M to WEEK 8 F
#8.3 | Preparing individual progress report, Preparing Weekly GANTT Chart, Reviewing not so important reference paper, Evaluating one team member’s individual progress report, Visiting Writing Center | Avani Mundra | 2023-10-10 | 2023-10-16 | 6 | Complete | bar: WEEK 8 M to WEEK 8 F
#8.4 | Preparing individual progress report, Evaluating one team member’s individual progress, studying not-so-important papers. | Justin Young | 2023-10-10 | 2023-10-16 | 6 | Complete | bar: WEEK 8 M to WEEK 8 F
#8.5 | Preparing individual progress report, Evaluating one team member’s individual progress and indivdual in-depth report, studying not-so-important papers. | Anuranjan Dubey | 2023-10-10 | 2023-10-16 | 6 | Complete | bar: WEEK 8 M to WEEK 8 F
#8.6 | Preparing individual progress report, Preparing individual in-depth report on refer paper [45], Preparing weekly report, Evaluating one team member’s individual progress reoprt, Visiting Writing Center | Rahul Rajarama Nayak | 2023-10-10 | 2023-10-16 | 6 | Complete | bar: WEEK 8 M to WEEK 8 F
#8.7 | Preparing individual progress report, Evaluating one team member’s individual progress report, Reviewing non-so-important reserach papers | Sangeeth Santhosh | 2023-10-10 | 2023-10-16 | 6 | Complete | bar: WEEK 8 M to WEEK 8 F
#8.8 | Preparing individual progress report,Preparing Weekly Report, Evaluating one team member’s individual progress report, Visiting Writing Center | Yeshwanth Reddy Chennur | 2023-10-10 | 2023-10-16 | 6 | Complete | bar: WEEK 8 M to WEEK 8 F